Case Study · Supply Chain # Automating a Mid-Sized Warehouse Without Losing Flexibility A phased move from paper picking to barcode scanning and zone picking

| ORGANISATION | SECTOR | PREPARED BY |
| --- | --- | --- |
| SwiftRoute Logistics (fictional) | Logistics | Case writer: Your Name |

# Contents

At a Glance	2

Background	3

The Challenge	3

Objectives	3

Approach	3

Phase 1: Location discipline	3

Phase 2: Scanning	4

Phase 3: System integration	4

Implementation Timeline	4

Results	4

Lessons Learned	5

Analysis	5

Discussion Questions	5

Teaching Note	6

Appendix: Additional Exhibits	6

Conclusion	6

# At a Glance

| Organisation | SwiftRoute Logistics (fictional) |
| --- | --- |
| Sector | Logistics |
| Location | Gurugram |
| Challenge | Picking errors and slow dispatch during peaks |
| Solution | Barcode scanning, zone picking and a warehouse management system |
| Timeframe | 8 months |

| 99.6% Picking accuracy (sample) | +35% Orders per shift | 8 mo Roll-out |
| --- | --- | --- |

Organisation and outcomes are illustrative; figures are sample data for teaching and templating purposes.

# Background

SwiftRoute operates a 1,20,000 sq ft fulfilment centre serving several e-commerce clients. Picking was done from printed lists, and stock locations were tracked in spreadsheets.

During festive peaks, errors and delays increased sharply, leading to penalties from clients.

# The Challenge

The company needed higher accuracy and throughput, but full robotic automation was too expensive and inflexible for its changing client mix.

Picking errors during peaks

Time lost searching for stock

Paper lists prone to mistakes

Limited real-time visibility for clients

We did not need robots; we needed every picker to know exactly where to go.

— Head of Operations (fictional)

# Objectives

Raise picking accuracy above 99.5%.

Increase orders processed per shift.

Give clients real-time inventory visibility.

# Approach

The project was delivered in phases so that operations never stopped.

## Phase 1: Location discipline

Every bin was labelled with a barcode and stock was re-slotted by sales velocity.

Bin labelling

ABC re-slotting

Cycle counts

## Phase 2: Scanning

Handheld scanners guided pickers and confirmed each item.

Scanner roll-out

Training

Exception handling

## Phase 3: System integration

A warehouse management system connected to client order platforms and provided dashboards.

WMS configuration

Client integrations

Dashboards

## Implementation Timeline

| Period | Milestone | Notes |
| --- | --- | --- |
| Month 1–2 | Labelling and re-slotting | Night shifts |
| Month 3–4 | Scanner pilot | One client |
| Month 5–7 | WMS roll-out | All clients |
| Month 8 | Stabilisation | Peak readiness review |

# Results

The warehouse handled the next festive peak with fewer errors and faster dispatch.

| Metric | Before | After |
| --- | --- | --- |
| Picking accuracy | 97.8% | 99.6% |
| Orders per shift | 2,600 | 3,500 |
| Average dispatch time (hrs) | 14 | 8 |
| Client penalties (per month) | 12 | 2 |

Exhibit 1: Key metrics before and after (sample data)

Chart placeholder — insert a before/after chart

Exhibit 2: Trend over the implementation period (sample data)

# Lessons Learned

Fix the basics first. Clean locations made scanning effective.

Train for exceptions. Most delays came from unusual cases, not normal picks.

Phase to protect service. Night-shift changes avoided disruption.

# Analysis

| What worked • Re-slotting by velocity • Supervisor dashboards | What was difficult • Data clean-up • Scanner battery management |
| --- | --- |
| Opportunities • Voice picking • Automated packing for top SKUs | Risks to sustain • Staff turnover • Client system changes |

# Discussion Questions

Use these questions for classroom discussion or self-study.

Why did the company choose scanning over robotic automation?

What is the value of re-slotting by sales velocity?

How would you plan staffing for a festive peak after these changes?

What metrics should the warehouse track daily?

# Teaching Note

Useful for supply chain and logistics courses. Students can compare the cost and flexibility of different automation options.

# Appendix: Additional Exhibits

| Error type | Share |
| --- | --- |
| Wrong item | 46% |
| Wrong quantity | 31% |
| Missed item | 15% |
| Other | 8% |

Exhibit 3: Error types before the project (%) (sample data)

# Conclusion

Targeted, phased automation delivered large gains while keeping the warehouse adaptable to new clients.