| 2026 | Case Study · Civil Engineering # Retrofitting a 40-Year-Old Road Bridge for Modern Traffic Loads Engineering assessment and strengthening of an ageing RCC bridge ORGANISATION District Public Works Division (illustrative) SECTOR Infrastructure PREPARED BY Case writer: Your Name |
| --- | --- |

# Contents

1. At a Glance	2

2. Background	3

3. The Challenge	3

4. Objectives	3

5. Approach	3

Phase 1: Condition assessment	4

Phase 2: Strengthening design	4

Phase 3: Execution	4

Implementation Timeline	4

6. Results	4

7. Lessons Learned	5

8. Analysis	5

9. Discussion Questions	5

10. Teaching Note	6

11. Appendix: Additional Exhibits	6

12. Conclusion	6

# 1. At a Glance

| Organisation | District Public Works Division (illustrative) |
| --- | --- |
| Sector | Infrastructure |
| Location | Central India |
| Challenge | Cracking, corrosion and higher traffic loads |
| Solution | Condition survey, carbon-fibre strengthening and bearing replacement |
| Timeframe | 14 months |

| 25+ yrs Extended service life (design) | −60% Closure time vs rebuild | 14 mo Project duration |
| --- | --- | --- |

Organisation and outcomes are illustrative; figures are sample data for teaching and templating purposes.

# 2. Background

The bridge is a four-span reinforced concrete structure built about forty years ago over a seasonal river. Traffic volumes and axle loads have increased greatly since it was designed.

Inspections showed cracking in the girders, spalling of concrete and corroded reinforcement in some areas.

# 3. The Challenge

Engineers had to decide whether to rebuild or strengthen the bridge, while keeping the route open as much as possible.

Visible cracks and spalling

Corroded reinforcement

Worn-out bearings

Only one alternative route, much longer

Replacing the bridge would have cut off villages for over a year.

— Executive Engineer (illustrative)

# 4. Objectives

Assess structural condition accurately.

Restore and enhance load capacity.

Minimise disruption to traffic.

# 5. Approach

The project followed a structured assessment and design process before any repair work.

## Phase 1: Condition assessment

Visual inspection, rebound hammer and ultrasonic tests, cover meter surveys and core samples.

Non-destructive testing

Core tests

Load rating analysis

## Phase 2: Strengthening design

Engineers designed carbon-fibre reinforced polymer wrapping for girders and repairs for damaged concrete.

Repair mortar specification

FRP design

Bearing replacement plan

## Phase 3: Execution

Work was done span by span with one-lane traffic and night closures for bearing replacement.

Surface preparation

FRP application

Jacking and bearing replacement

## Implementation Timeline

| Period | Milestone | Notes |
| --- | --- | --- |
| Month 1–3 | Assessment and testing | Report and load rating |
| Month 4–5 | Design and approvals | Drawings and specifications |
| Month 6–12 | Strengthening works | Span by span |
| Month 13–14 | Load test and handover | Monitoring plan |

# 6. Results

The strengthened bridge passed a load test and returned to full service.

| Parameter | Before | After |
| --- | --- | --- |
| Load rating (relative) | 0.78 | 1.15 |
| Crack width (max, mm) | 0.6 | Sealed |
| Deflection under test load (mm) | — | Within limits |
| Full closure days | — | 9 |

Exhibit 1: Key metrics before and after (sample data)

Chart placeholder — insert a before/after chart

Exhibit 2: Trend over the implementation period (sample data)

# 7. Lessons Learned

Test before deciding. Detailed testing showed the structure could be saved.

Plan traffic carefully. Span-by-span work kept the route open.

Monitor after repair. Sensors and inspections protect the investment.

# 8. Analysis

| What worked • Accurate testing • Phased execution | What was difficult • Monsoon interruptions • Quality control of FRP |
| --- | --- |
| Opportunities • Apply method to other bridges • Digital monitoring | Risks to sustain • Overloaded trucks • Maintenance budgets |

# 9. Discussion Questions

Use these questions for classroom discussion or self-study.

What information is needed to choose between repair and replacement?

Why was FRP selected for strengthening?

How would you manage traffic during the works?

What should the maintenance plan include?

# 10. Teaching Note

Suitable for courses in structural engineering, construction management and infrastructure policy.

# 11. Appendix: Additional Exhibits

| Test | Location | Result |
| --- | --- | --- |
| Rebound hammer | Girders | Fair to good |
| Ultrasonic pulse velocity | Girders | Medium quality |
| Cover meter | Soffit | Low cover in places |
| Carbonation depth | Cores | Reached reinforcement in places |

Exhibit 3: Test results summary (sample data)

# 12. Conclusion

A careful engineering assessment allowed the bridge to be strengthened at lower cost and disruption than replacement.