Case Study · Operations Management

# Cutting Patient Waiting Time at a City Hospital Outpatient Department

Applying process mapping and digital token systems in a busy OPD

| ORGANISATION | SECTOR | PREPARED BY |
| --- | --- | --- |
| Shanti City Hospital (fictional) | Healthcare | Case writer: Your Name |

# Contents

At a Glance	3

Background	4

The Challenge	4

Objectives	4

Approach	5

Phase 1: Map the process	5

Phase 2: Redesign	5

Phase 3: Digitise	5

Implementation Timeline	5

Results	6

Lessons Learned	6

Analysis	6

Discussion Questions	7

Teaching Note	7

Appendix: Additional Exhibits	7

Conclusion	8

# At a Glance

| Organisation | Shanti City Hospital (fictional) |
| --- | --- |
| Sector | Healthcare |
| Location | Nagpur |
| Challenge | Average OPD waits of over two hours |
| Solution | Process redesign, staggered appointments and a digital token system |
| Timeframe | 6 months |

| −55% Average waiting time (sample) | +22% Patients seen per day | 6 mo Project duration |
| --- | --- | --- |

Organisation and outcomes are illustrative; figures are sample data for teaching and templating purposes.

# Background

Shanti City Hospital is a 250-bed multi-specialty hospital whose outpatient department sees a large number of patients every day. Most arrive in the morning, creating long queues at registration, billing and consultation rooms.

Patient complaints about waiting time had become the most common feedback, and doctors were frustrated by unpredictable workloads.

# The Challenge

Management wanted to reduce waiting time without hiring many more staff or expanding the building.

Morning peak with most patients arriving between 9 and 11 AM

Separate queues for registration, billing and consultation

Paper files moved by hand between counters

No visibility of waiting time for patients

Patients were spending more time in queues than with their doctors.

— Medical Superintendent (fictional)

# Objectives

Reduce average waiting time by half.

Spread patient arrivals across the day.

Improve patient and staff satisfaction.

# Approach

A small team of administrators, nurses and an industrial engineering intern mapped the patient journey and tested improvements in two departments before scaling.

## Phase 1: Map the process

The team timed each step for 300 patients and drew a value-stream map. Most time was spent waiting between steps rather than in service.

Time study

Value-stream map

Bottleneck analysis

## Phase 2: Redesign

Registration and billing were combined at a single counter, and appointment slots were staggered in 15-minute intervals.

Single-window registration

Staggered appointments

Pre-registration by phone

## Phase 3: Digitise

A token display system and SMS updates told patients their expected time, so they could wait comfortably or step out.

Token display screens

SMS notifications

Electronic files

## Implementation Timeline

| Period | Milestone | Notes |
| --- | --- | --- |
| Month 1 | Process mapping | Two pilot departments |
| Month 2–3 | Redesign pilot | Single window and slots |
| Month 4 | Token system installed | Staff training |
| Month 5–6 | Scale-up | All OPD departments |

# Results

Waiting time fell sharply, and the department handled more patients with the same staff.

| Metric | Before | After |
| --- | --- | --- |
| Average waiting time (min) | 128 | 58 |
| Patients seen per day | 640 | 780 |
| Patient satisfaction (1–5) | 2.9 | 4.1 |
| Doctor idle time (min/day) | 45 | 18 |

Exhibit 1: Key metrics before and after (sample data)

Chart placeholder — insert a before/after chart

Exhibit 2: Trend over the implementation period (sample data)

# Lessons Learned

Measure first. Time studies revealed that waiting, not service, was the main problem.

Pilot, then scale. Testing in two departments built staff confidence.

Communicate with patients. Knowing their expected time reduced frustration even before waits fell.

# Analysis

| What worked • Combining counters • SMS updates | What was difficult • Patients unfamiliar with appointments • Initial staff resistance |
| --- | --- |
| Opportunities • Online pre-registration • Pharmacy integration | Risks to sustain • Peak seasons • Maintaining discipline in slots |

# Discussion Questions

Use these questions for classroom discussion or self-study.

Where did most of the waiting time come from, and why?

How did staggered appointments change the arrival pattern?

What would you do if patients ignored appointment slots?

How could the same approach be applied to a diagnostic laboratory?

# Teaching Note

The case is suitable for operations management and healthcare administration courses. Students can be asked to draw the before and after process maps and to calculate utilisation of each counter.

# Appendix: Additional Exhibits

| Step | Before | After |
| --- | --- | --- |
| Registration | 25 | 8 |
| Billing | 20 | 0 (merged) |
| Waiting for doctor | 70 | 40 |
| Consultation | 12 | 12 |

Exhibit 3: Time spent at each step (minutes) (sample data)

| Hour | Before | After |
| --- | --- | --- |
| 9–10 AM | 38% | 18% |
| 10–11 AM | 30% | 20% |
| 11 AM–1 PM | 20% | 32% |
| After 1 PM | 12% | 30% |

Exhibit 4: Arrivals by hour (% of patients) (sample data)

# Conclusion

The hospital improved patient experience significantly through simple process changes supported by modest technology.