	Your Institute of Technology
TechVerse Organising Committee
	MINUTES
Ref: YIT/TV26/M05


	



TechVerse 2026 — Core Committee Meeting
	Date
	Wednesday, 7 January 2026

	Time
	5:00 PM – 6:15 PM

	Venue
	Student Activity Centre

	Chaired by
	Riya Sharma, General Secretary

	Minutes recorded by
	Ishaan Gupta, Joint Secretary



Attendance
	Name
	Role
	Status

	Riya Sharma
	General Secretary
	Present

	Ishaan Gupta
	Joint Secretary
	Present

	Aditya Rao
	Sponsorship Head
	Present

	Kavya Iyer
	Events Head
	Present

	Zoya Khan
	Publicity Head
	Present

	Prof. S. Banerjee
	Faculty Adviser
	Present



Agenda
Sponsorship status
Event list
Publicity
Hospitality
Discussion and Decisions
1. Sponsorship status
Two partners have confirmed and three are in discussion.
Decision: Follow up with pending partners by 15 January.
2. Event list
The events team proposed 26 events. Two overlapping events were merged.
Decision: Final list of 25 events approved.
3. Publicity
Social media teasers will start next week; posters for partner colleges are ready.
Decision: Begin campaign on 12 January.
4. Hospitality
Accommodation for outstation participants needs hostel approval.
Decision: Faculty adviser to request approval from the warden.
Action Items
	#
	Action
	Owner
	Due date
	Status

	1
	Follow up with sponsors
	Aditya Rao
	15 Jan 2026
	Open

	2
	Publish event list
	Kavya Iyer
	10 Jan 2026
	Open

	3
	Start teaser campaign
	Zoya Khan
	12 Jan 2026
	Open

	4
	Hostel approval
	Prof. S. Banerjee
	14 Jan 2026
	Open



Next Meeting
Next meeting: Wednesday, 14 January 2026 at 5:00 PM.
The meeting ended at 6:15 PM with a vote of thanks by the chair.

	____________________
	____________________

	Riya Sharma
Chairperson
	Ishaan Gupta
Recorded by



Minutes are a summary of the discussion and are confirmed at the next meeting. Circulate within three working days.
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