| Your Institute of Technology TechVerse Organising Committee | MINUTES Ref: YIT/TV26/M05 |
| --- | --- |

# TechVerse 2026 — Core Committee Meeting

| Date | Wednesday, 7 January 2026 |
| --- | --- |
| Time | 5:00 PM – 6:15 PM |
| Venue | Student Activity Centre |
| Chaired by | Riya Sharma, General Secretary |
| Minutes recorded by | Ishaan Gupta, Joint Secretary |

## Attendance

| Name | Role | Status |
| --- | --- | --- |
| Riya Sharma | General Secretary | Present |
| Ishaan Gupta | Joint Secretary | Present |
| Aditya Rao | Sponsorship Head | Present |
| Kavya Iyer | Events Head | Present |
| Zoya Khan | Publicity Head | Present |
| Prof. S. Banerjee | Faculty Adviser | Present |

## Agenda

Sponsorship status

Event list

Publicity

Hospitality

## Discussion and Decisions

1. Sponsorship status

Two partners have confirmed and three are in discussion.

Decision: Follow up with pending partners by 15 January.

2. Event list

The events team proposed 26 events. Two overlapping events were merged.

Decision: Final list of 25 events approved.

3. Publicity

Social media teasers will start next week; posters for partner colleges are ready.

Decision: Begin campaign on 12 January.

4. Hospitality

Accommodation for outstation participants needs hostel approval.

Decision: Faculty adviser to request approval from the warden.

## Action Items

| # | Action | Owner | Due date | Status |
| --- | --- | --- | --- | --- |
| 1 | Follow up with sponsors | Aditya Rao | 15 Jan 2026 | Open |
| 2 | Publish event list | Kavya Iyer | 10 Jan 2026 | Open |
| 3 | Start teaser campaign | Zoya Khan | 12 Jan 2026 | Open |
| 4 | Hostel approval | Prof. S. Banerjee | 14 Jan 2026 | Open |

## Next Meeting

Next meeting: Wednesday, 14 January 2026 at 5:00 PM.

The meeting ended at 6:15 PM with a vote of thanks by the chair.

| ____________________ | ____________________ |
| --- | --- |
| Riya Sharma Chairperson | Ishaan Gupta Recorded by |

Minutes are a summary of the discussion and are confirmed at the next meeting. Circulate within three working days.