| Sahyog Foundation Programme Review | MINUTES Ref: SF/PR/2026/Q2 |
| --- | --- |

# Quarterly Programme Review — Digital Literacy

| Date | Thursday, 9 July 2026 |
| --- | --- |
| Time | 2:30 PM – 4:30 PM |
| Venue | Foundation office and video call |
| Chaired by | Rekha Iyer, Programme Director |
| Minutes recorded by | Anil Patil, M&E Officer |

## Attendance

| Name | Role | Status |
| --- | --- | --- |
| Rekha Iyer | Programme Director | Present |
| Anil Patil | M&E Officer | Present |
| Field coordinators (2) | Coordination | Present |
| Community trainers (5) | Trainer representatives | Present |
| Donor representative | Partner | Video call |

## Agenda

Progress against plan

Learning outcomes

Trainer feedback

Budget utilisation

## Discussion and Decisions

1. Progress against plan

Training batches are on schedule in 14 of 20 villages; six villages were delayed by the sowing season.

Decision: Shift sessions in delayed villages to evenings.

2. Learning outcomes

Post-training quizzes show good understanding of payments; online selling needs more practice.

Decision: Add two practice sessions on product listing.

3. Trainer feedback

Trainers requested printed practice cards in the local language.

Decision: Print practice cards this month.

4. Budget utilisation

Spending is in line with plan; device purchase was slightly under budget.

Decision: Reallocate savings to printing.

## Action Items

| # | Action | Owner | Due date | Status |
| --- | --- | --- | --- | --- |
| 1 | Revise village schedules | Field coordinators | 20 Jul 2026 | Open |
| 2 | Design extra listing sessions | Rekha Iyer | 25 Jul 2026 | Open |
| 3 | Print practice cards | Anil Patil | 31 Jul 2026 | Open |
| 4 | Share quarterly report with donor | Rekha Iyer | 15 Jul 2026 | Open |

## Next Meeting

Next review: October 2026.

The meeting ended at 4:30 PM with a vote of thanks by the chair.

| ____________________ | ____________________ |
| --- | --- |
| Rekha Iyer Chairperson | Anil Patil Recorded by |

Minutes are a summary of the discussion and are confirmed at the next meeting. Circulate within three working days.