| Your Startup Pvt. Ltd. Founders & Leadership | MINUTES Ref: YS/LT/2026/Q2 |
| --- | --- |

# Quarterly Business Review — Q2 FY 2026–27

| Date | Friday, 3 July 2026 |
| --- | --- |
| Time | 10:00 AM – 1:00 PM |
| Venue | Board Room / video call |
| Chaired by | Founder Name, CEO |
| Minutes recorded by | Associate Name, Chief of Staff |

## Attendance

| Name | Role | Status |
| --- | --- | --- |
| Founder Name | Co-founder & CEO | Present |
| Co-founder Name | Co-founder & CTO | Present |
| Finance Head Name | Head of Finance | Present |
| Growth Head Name | Head of Growth | Present |
| Ops Head Name | Head of Operations | Remote |
| Associate Name | Chief of Staff | Present |

## Agenda

Revenue

Burn and runway

Product

Hiring

## Discussion and Decisions

1. Revenue

Q2 revenue was ₹3.4 crore (sample figure), 8% below plan, mainly because two enterprise deals moved to Q3.

Decision: Sales to share a weekly pipeline update with the CEO.

2. Burn and runway

Monthly burn is ₹62 lakh; runway is 14 months at the current rate.

Decision: Freeze non-critical hiring until Q3 numbers are clear.

3. Product

The new onboarding flow cut drop-off at sign-up from 41% to 29%.

Decision: Roll out the flow to all customers by 31 July.

4. Hiring

Three of five planned engineering hires have joined.

Decision: Close the remaining two roles; pause the design hire.

## Action Items

| # | Action | Owner | Due date | Status |
| --- | --- | --- | --- | --- |
| 1 | Weekly pipeline update | Growth Head Name | Every Monday | Open |
| 2 | Hiring freeze note to managers | Finance Head Name | 7 Jul 2026 | Open |
| 3 | Onboarding flow roll-out | Co-founder Name | 31 Jul 2026 | In progress |
| 4 | Revised Q3 forecast | Finance Head Name | 15 Jul 2026 | Open |

## Next Meeting

Next review: Friday, 2 October 2026, 10:00 AM.

The meeting ended at 1:00 PM with a vote of thanks by the chair.

| ____________________ | ____________________ |
| --- | --- |
| Founder Name Chairperson | Associate Name Recorded by |

Minutes are a summary of the discussion and are confirmed at the next meeting. Circulate within three working days.