| Shubh Laabh Traders Association Executive Committee | MINUTES Ref: SLTA/EC/2026/06 |
| --- | --- |

# Executive Committee Meeting — Diwali Market Arrangements

| Date | Sunday, 20 September 2026 |
| --- | --- |
| Time | 6:00 PM – 7:30 PM |
| Venue | Association Hall, Main Bazaar |
| Chaired by | Mr. President Name, President |
| Minutes recorded by | Mr. Secretary Name, General Secretary |

## Attendance

| Name | Role | Status |
| --- | --- | --- |
| Mr. President Name | President | Present |
| Mr. Secretary Name | General Secretary | Present |
| Mrs. Treasurer Name | Treasurer | Present |
| Mr. Member Name | Executive member | Present |
| Mr. Member Name | Executive member | Present |
| Ms. Member Name | Executive member | Remote |

## Agenda

Decoration and lighting

Parking and traffic

Safety

Lucky draw

## Discussion and Decisions

1. Decoration and lighting

Last year's lighting contract cost ₹2.8 lakh (sample figure). Three new quotes have been received.

Decision: Treasurer and two members to finalise the vendor by 30 September.

2. Parking and traffic

Shoppers complained about parking during the festival week.

Decision: Request the traffic police for one-way rules and a temporary parking lot near the school ground.

3. Safety

Fire extinguishers in several shops are past their refill date.

Decision: All members to refill extinguishers; the association will arrange a bulk refill camp.

4. Lucky draw

Members agreed to run a lucky draw for shoppers to increase footfall.

Decision: Draw on 8 November; coupons to be printed by 15 October.

## Action Items

| # | Action | Owner | Due date | Status |
| --- | --- | --- | --- | --- |
| 1 | Finalise lighting vendor | Mrs. Treasurer Name | 30 Sep 2026 | Open |
| 2 | Letter to traffic police | Mr. Secretary Name | 25 Sep 2026 | Open |
| 3 | Extinguisher refill camp | Mr. Member Name | 5 Oct 2026 | Open |
| 4 | Print lucky-draw coupons | Ms. Member Name | 15 Oct 2026 | Open |

## Next Meeting

Next meeting: Sunday, 4 October 2026, 6:00 PM.

The meeting ended at 7:30 PM with a vote of thanks by the chair.

| ____________________ | ____________________ |
| --- | --- |
| Mr. President Name Chairperson | Mr. Secretary Name Recorded by |

Minutes are a summary of the discussion and are confirmed at the next meeting. Circulate within three working days.