Project Proposal

# Rooftop Rainwater Harvesting for Green Valley Society

Proposal to capture and reuse rooftop rainwater across six residential towers

| PREPARED FOR | PREPARED BY | DATE |
| --- | --- | --- |
| Managing Committee and Residents | Suresh Nair, Environment Sub-committee | January 2026 |

# Contents

01  Executive Summary	2

02  Background and Need	3

03  Goals and Objectives	3

04  Approach and Activities	3

Site survey	3

Design	3

Installation	3

Awareness	3

Deliverables	3

05  Timeline	4

06  Team and Governance	4

07  Budget	4

08  Monitoring and Evaluation	5

09  Risks and Mitigation	5

10  Conclusion	5

# 01  Executive Summary

Green Valley buys water tankers every summer while most monsoon rainwater from our rooftops flows into storm drains. This proposal recommends a rooftop rainwater harvesting system with filtration and recharge pits for all six towers, reducing tanker dependence and recharging groundwater.

| 6 towers Covered | ₹7.8 L Estimated cost | 3 months Installation |
| --- | --- | --- |

# 02  Background and Need

Water demand in the society has risen while borewell levels have fallen. In the last two summers the society spent heavily on tankers.

The combined rooftop area of the towers can capture a large volume of rainwater each monsoon, which is currently wasted.

# 03  Goals and Objectives

Harvest rooftop rainwater to reduce tanker purchases and recharge groundwater.

Install collection, filtration and recharge systems for all towers.

Reduce summer tanker purchases.

Raise residents’ awareness of water conservation.

# 04  Approach and Activities

## Site survey

Measure rooftop areas, downpipes and suitable pit locations.

## Design

Size filters, storage and recharge pits with a qualified consultant.

## Installation

Phased work tower by tower with minimum disruption.

## Awareness

Information sessions and notice-board updates for residents.

## Deliverables

| Deliverable | Description | Due |
| --- | --- | --- |
| Survey report | Roof areas and layout | Month 1 |
| Approved design | Drawings and bill of quantities | Month 1 |
| Installed systems | All six towers | Month 3 |
| Maintenance plan | Cleaning schedule and responsibilities | Month 3 |

# 05  Timeline

The work plan below shows the main activities and their indicative timing.

| Activity | Jan | Feb | Mar | Apr |
| --- | --- | --- | --- | --- |
| Survey and design | ■ |  |  |  |
| Vendor selection | ■ | ■ |  |  |
| Installation |  | ■ | ■ |  |
| Testing and handover |  |  |  | ■ |

# 06  Team and Governance

| Name | Role | Responsibility |
| --- | --- | --- |
| Suresh Nair | Coordinator | Planning and vendor coordination |
| Meena Joshi | Treasurer | Budget and payments |
| Consultant (to be appointed) | Technical expert | Design and supervision |
| Tower representatives | Liaisons | Resident communication |

# 07  Budget

All amounts are estimates in Indian rupees and are provided as sample figures for planning.

| Head | Details | Amount (₹) |
| --- | --- | --- |
| Consultant fees | Survey, design and supervision | 60,000 |
| Filters and piping | Six towers | 280,000 |
| Recharge pits | Eight pits with filter media | 320,000 |
| Civil work | Excavation and restoration | 90,000 |
| Contingency | Unforeseen items | 30,000 |
| Total |  | 780,000 |

# 08  Monitoring and Evaluation

| Indicator | Target | How measured |
| --- | --- | --- |
| Systems installed | 6 of 6 | Completion certificate |
| Tanker purchases | Lower than last summer | Accounts records |
| Borewell level | Stable or rising | Pre- and post-monsoon readings |

# 09  Risks and Mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Delay due to early rain | Medium | Start work in January |
| Cost overrun | Low | Fixed-price contract |
| Poor maintenance | Medium | Annual maintenance contract and checklist |

# 10  Conclusion

Rainwater harvesting is a long-term investment in our water security. We recommend approval at the next general body meeting.

Next step Approve the proposal and authorise the committee to invite quotations.

| ____________________ | ____________________ |
| --- | --- |
| Suresh Nair Submitted by | Approved by (name, designation) |