Sahyog Foundation

Grant Proposal

# Digital Literacy for Rural Women Entrepreneurs

A 12-month programme to train 600 women in self-help groups to use smartphones for business

| PREPARED FOR | PREPARED BY | DATE |
| --- | --- | --- |
| CSR Committee, Your Partner Company | Rekha Iyer, Programme Director | April 2026 |

# Contents

1. Executive Summary	2

2. Background and Need	3

3. Goals and Objectives	3

4. Approach and Activities	3

Baseline survey	3

Trainer development	3

Village sessions	4

Market linkage	4

Follow-up	4

Deliverables	4

5. Timeline	4

6. Team and Governance	4

7. Budget	5

8. Monitoring and Evaluation	5

9. Risks and Mitigation	6

10. Sustainability	6

11. About Sahyog Foundation	6

12. Conclusion	6

13. Annexure: Contact Details	7

# 1. Executive Summary

Women running small enterprises in self-help groups often cannot use digital payments, online marketplaces or government portals, which limits their income. Sahyog Foundation seeks a grant to train 600 women across 20 villages in practical digital skills — payments, record keeping, online selling and safety — through community trainers and hands-on practice.

| 600 Women trained | 20 Villages | 12 months Duration |
| --- | --- | --- |

# 2. Background and Need

Many self-help group members own or share a smartphone but use it mainly for calls. Lack of confidence and language barriers keep them away from digital tools that could expand their business.

Our baseline visits (sample findings) showed that fewer than one in five members had made a digital payment on their own.

Limited confidence with smartphones

Fear of online fraud

Few trainers who speak the local language

# 3. Goals and Objectives

Enable women entrepreneurs to use digital tools confidently and safely to grow their businesses.

Train 600 women in digital payments, record keeping and online selling.

Develop 20 local women as community digital trainers.

Help at least 200 participants list products on an online platform.

Promote safe online practices and fraud awareness.

# 4. Approach and Activities

## Baseline survey

Assess skills, device access and business needs in each village.

## Trainer development

Train 20 community trainers through a 10-day programme.

## Village sessions

Twelve weekly sessions per batch with practice tasks in the local language.

## Market linkage

Support product photography, listing and order handling.

## Follow-up

Monthly help desks and refresher sessions.

## Deliverables

| Deliverable | Description | Due |
| --- | --- | --- |
| Baseline report | Skills and needs assessment | Month 2 |
| Training toolkit | Modules, videos, practice cards | Month 3 |
| Trained participants | 600 women | Month 11 |
| Endline report | Outcomes and learning | Month 12 |

# 5. Timeline

The work plan below shows the main activities and their indicative timing.

| Activity | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| Baseline and toolkit | ■ |  |  |  |
| Trainer development | ■ | ■ |  |  |
| Village sessions |  | ■ | ■ | ■ |
| Market linkage |  |  | ■ | ■ |
| Evaluation |  |  |  | ■ |

# 6. Team and Governance

| Name | Role | Responsibility |
| --- | --- | --- |
| Rekha Iyer | Programme director | Overall delivery |
| Field coordinators (2) | Coordination | Village planning and monitoring |
| Community trainers (20) | Trainers | Sessions and follow-up |
| M&E officer | Evaluation | Data and reporting |

The foundation’s board will review quarterly progress; the donor will receive quarterly narrative and financial reports.

# 7. Budget

All amounts are estimates in Indian rupees and are provided as sample figures for planning.

| Head | Details | Amount (₹) |
| --- | --- | --- |
| Personnel | Director (part), coordinators, M&E | 1,450,000 |
| Trainer stipends | 20 trainers × 12 months | 720,000 |
| Training material | Toolkits and videos | 180,000 |
| Devices for practice | 40 shared smartphones | 320,000 |
| Travel | Field visits | 260,000 |
| Admin and audit | Overheads (7%) | 205,000 |
| Total |  | 3,135,000 |

# 8. Monitoring and Evaluation

| Indicator | Target | How measured |
| --- | --- | --- |
| Women trained | 600 | Attendance records |
| Digital payment use | 70% of trained women | Endline survey |
| Online listings | 200 enterprises | Platform records |
| Fraud awareness | 90% can identify common scams | Post-training quiz |

# 9. Risks and Mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Low attendance during harvest | High | Flexible timing and shorter sessions |
| Device sharing within families | Medium | Shared practice phones at centres |
| Connectivity | Medium | Offline content and data packs |

# 10. Sustainability

Community trainers will continue to offer paid help-desk services after the project, and the toolkit will be shared openly with other organisations.

# 11. About Sahyog Foundation

Sahyog Foundation is a registered non-profit working on livelihoods and women’s empowerment in rural areas. (Replace with your organisation’s registration details, track record and audited financials.)

# 12. Conclusion

With your support, 600 women will gain skills that directly increase their income and independence.

Next step Consider a grant of ₹31.35 lakh for the 12-month programme; we would be glad to present the plan in person.

| ____________________ | ____________________ |
| --- | --- |
| Rekha Iyer Submitted by | Approved by (name, designation) |

# 13. Annexure: Contact Details

| Organisation | Sahyog Foundation |
| --- | --- |
| Contact person | Rekha Iyer, Programme Director |
| Email | contact@yourdomain.in |
| Phone | +91 00000 00000 |
| Address | Your address line, City, PIN |