2026

Grant Proposal # Community Health Worker Training for Maternal Care Strengthening antenatal and postnatal care in 25 urban settlements

| PREPARED FOR | PREPARED BY | DATE |
| --- | --- | --- |
| Programme Officer, Your Funding Foundation | Dr. Farah Siddiqui, Medical Director | March 2026 |

# Contents

Executive Summary	3

Background and Need	4

Goals and Objectives	4

Approach and Activities	4

Volunteer selection and training	4

Household visits	4

Referral support	4

Community sessions	4

Deliverables	5

Timeline	5

Team and Governance	5

Budget	6

Monitoring and Evaluation	6

Risks and Mitigation	6

Sustainability	7

Conclusion	7

# Executive Summary

Many pregnant women in informal urban settlements miss antenatal check-ups and do not recognise danger signs. Asha Kiran Health Trust proposes to train 75 community health volunteers to track pregnancies, counsel families, accompany women to clinics and follow up after delivery, linking households with existing public health services.

| 75 Volunteers trained | 25 Settlements | 18 months Duration |
| --- | --- | --- |

# Background and Need

Women in these settlements often work daily-wage jobs and cannot easily visit clinics. Information about danger signs and nutrition is limited.

Public health services exist, but families may not know how to access them. Trained volunteers from the same community can bridge this gap.

# Goals and Objectives

Increase timely antenatal and postnatal care for women in 25 settlements.

Train 75 volunteers in maternal health, counselling and record keeping.

Register pregnancies early and track check-ups.

Accompany high-risk women to health facilities.

Conduct community awareness sessions on nutrition and danger signs.

# Approach and Activities

## Volunteer selection and training

Select women trusted in the community and train them over 15 days.

## Household visits

Monthly visits to registered pregnant women and new mothers.

## Referral support

Accompany high-risk cases and follow up after referral.

## Community sessions

Monthly group sessions on nutrition, hygiene and newborn care.

## Deliverables

| Deliverable | Description | Due |
| --- | --- | --- |
| Training curriculum | Modules and job aids | Month 2 |
| Trained volunteers | 75 | Month 3 |
| Pregnancy register | Digital tracking sheet | Month 4 |
| Final evaluation | Outcomes and lessons | Month 18 |

# Timeline

The work plan below shows the main activities and their indicative timing.

| Activity | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 |
| --- | --- | --- | --- | --- | --- | --- |
| Selection and training | ■ |  |  |  |  |  |
| Household visits |  | ■ | ■ | ■ | ■ | ■ |
| Community sessions |  | ■ | ■ | ■ | ■ | ■ |
| Mid-term review |  |  | ■ |  |  |  |
| Evaluation |  |  |  |  |  | ■ |

# Team and Governance

| Name | Role | Responsibility |
| --- | --- | --- |
| Dr. Farah Siddiqui | Medical director | Clinical oversight |
| Programme manager | Manager | Operations and partnerships |
| Supervisors (5) | Supervisors | Support volunteers |
| Health volunteers (75) | Volunteers | Visits and referrals |

# Budget

All amounts are estimates in Indian rupees and are provided as sample figures for planning.

| Head | Details | Amount (₹) |
| --- | --- | --- |
| Training | Curriculum, venue, trainers | 380,000 |
| Volunteer honorarium | 75 × 18 months | 1,350,000 |
| Supervisors | 5 × 18 months | 900,000 |
| Job aids and registers | Printing and phones | 220,000 |
| Community sessions | Materials and refreshments | 180,000 |
| Evaluation and admin | External evaluation, overheads | 300,000 |
| Total |  | 3,330,000 |

# Monitoring and Evaluation

| Indicator | Target | How measured |
| --- | --- | --- |
| Early registration | 80% in first trimester | Register |
| Four or more check-ups | 75% of women | Clinic cards |
| Postnatal visits | 90% within 7 days | Visit logs |
| Volunteer retention | 85% | HR records |

# Risks and Mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Volunteer drop-out | Medium | Honorarium and recognition |
| Migration of families | Medium | Handover between settlements |
| Data privacy | Low | Consent and coded records |

# Sustainability

Volunteers will be linked with the public health system’s community programmes, and the trust will seek municipal support to continue honoraria.

# Conclusion

Trained community volunteers can make a measurable difference to the health of mothers and newborns.

Next step Approve a grant of ₹33.3 lakh over 18 months.

| ____________________ | ____________________ |
| --- | --- |
| Dr. Farah Siddiqui Submitted by | Approved by (name, designation) |