Event Proposal

# TechVerse 2026 — Annual Technical Fest

Sponsorship proposal for a two-day inter-college technical festival

| PREPARED FOR | PREPARED BY | DATE |
| --- | --- | --- |
| Prospective Sponsors and Partners | Riya Sharma, General Secretary | December 2025 |

# Contents

01  Executive Summary	2

02  Event Concept	3

03  Goals and Objectives	3

04  Event Details	3

Programme Schedule	3

Target Audience	4

05  Sponsorship Opportunities	4

Promotion Plan	4

Logistics and Operations	4

06  Timeline	5

07  Team and Governance	5

08  Budget	5

09  Measuring Success	6

10  Risks and Mitigation	6

11  Conclusion	6

12  Annexure: Contact Details	7

# 01  Executive Summary

TechVerse is the annual technical festival of Your Institute of Technology, bringing together students from colleges across the region for competitions, workshops and talks. This proposal invites organisations to partner with TechVerse 2026 and connect with a large audience of engineering students.

| 2 days 6–7 Feb 2026 | 25+ Events | Regional Colleges invited |
| --- | --- | --- |

# 02  Event Concept

TechVerse gives students a platform to build, compete and learn beyond the classroom. It also gives partners a chance to meet talented students, promote internships and showcase products.

Each edition is planned and run entirely by students, supported by faculty advisers.

# 03  Goals and Objectives

Organise a well-run, inclusive technical festival that celebrates innovation and connects students with industry.

Host competitions in coding, robotics, design and entrepreneurship.

Run hands-on workshops led by practitioners.

Provide sponsors with meaningful engagement with students.

Ensure a safe, accessible event for all participants.

# 04  Event Details

| Dates | 6–7 February 2026 |
| --- | --- |
| Venue | Main campus, Your Institute of Technology |
| Expected footfall | Several thousand visitors over two days (estimate) |
| Participants | Students from colleges across the region |
| Organisers | Student Council with faculty advisers |

## Programme Schedule

| Time | Session | Venue / format |
| --- | --- | --- |
| Day 1, 9:30 AM | Inauguration and keynote talk | Main auditorium |
| Day 1, 11:00 AM | Hackathon kick-off (24 hours) | Computer centre |
| Day 1, 2:00 PM | Robotics challenge — heats | Sports complex |
| Day 1, 4:00 PM | Workshop: Intro to IoT | Lab block |
| Day 2, 10:00 AM | Startup pitch competition | Seminar hall |
| Day 2, 1:00 PM | Robotics finals | Sports complex |
| Day 2, 5:00 PM | Prize distribution and closing | Main auditorium |

## Target Audience

Undergraduate and postgraduate engineering students

Faculty members and researchers

Early-stage founders and alumni

# 05  Sponsorship Opportunities

Sponsors receive visibility before, during and after the event. Packages can be customised; amounts below are indicative.

| Tier | Contribution | Key benefits |
| --- | --- | --- |
| Title partner | ₹3,00,000 | Name in event title, keynote slot, logo on all material, stall |
| Platinum | ₹1,50,000 | Logo on banners and website, stall, workshop slot |
| Gold | ₹75,000 | Logo on banners, social media mentions, stall |
| Event partner | ₹40,000 | Naming of one competition, prize distribution |
| In-kind partner | Products / services | Acknowledgement and stall |

## Promotion Plan

Social media campaign for six weeks before the fest

Posters and campus ambassadors in partner colleges

Email and newsletter to past participants

Live coverage during the event

## Logistics and Operations

| Area | Plan | Owner |
| --- | --- | --- |
| Registration | Online registration with QR entry passes | Registration team |
| Security | Volunteers and campus security at all gates | Discipline committee |
| Hospitality | Accommodation for outstation participants | Hospitality team |
| Medical | First-aid post and ambulance on call | Medical team |

# 06  Timeline

The work plan below shows the main activities and their indicative timing.

| Activity | Oct | Nov | Dec | Jan | Feb |
| --- | --- | --- | --- | --- | --- |
| Planning and approvals | ■ | ■ |  |  |  |
| Sponsorship drive |  | ■ | ■ | ■ |  |
| Promotion |  |  | ■ | ■ | ■ |
| Event execution |  |  |  |  | ■ |
| Post-event report |  |  |  |  | ■ |

# 07  Team and Governance

| Name | Role | Responsibility |
| --- | --- | --- |
| Riya Sharma | General Secretary | Overall coordination |
| Aditya Rao | Sponsorship head | Partner relations |
| Kavya Iyer | Events head | Competitions and schedule |
| Prof. S. Banerjee | Faculty adviser | Guidance and approvals |

# 08  Budget

All amounts are estimates in Indian rupees and are provided as sample figures for planning.

| Head | Details | Amount (₹) |
| --- | --- | --- |
| Venue and infrastructure | Stage, sound, lighting | 350,000 |
| Prizes | Competition prizes | 250,000 |
| Hospitality | Food and accommodation | 220,000 |
| Promotion | Printing and digital | 90,000 |
| Workshops | Kits and speaker travel | 120,000 |
| Miscellaneous | Contingency | 70,000 |
| Total |  | 1,100,000 |

# 09  Measuring Success

| Indicator | Target | How measured |
| --- | --- | --- |
| Registrations | Target set by council | Registration system |
| Sponsor leads | Contacts shared with consent | Lead forms |
| Participant feedback | 4 / 5 or higher | Post-event survey |

# 10  Risks and Mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Weather or power failure | Low | Backup generator and indoor venues |
| Over-crowding | Medium | Entry passes and crowd plan |
| Speaker cancellation | Low | Backup speakers |

# 11  Conclusion

Partnering with TechVerse 2026 is an opportunity to engage directly with motivated, skilled students and support innovation on campus.

Next step Choose a sponsorship tier or suggest a custom partnership; we will share the agreement and branding guidelines.

| ____________________ | ____________________ |
| --- | --- |
| Riya Sharma Submitted by | Approved by (name, designation) |

# 12  Annexure: Contact Details

| Organisation | Student Council, Your Institute of Technology |
| --- | --- |
| Contact person | Riya Sharma, General Secretary |
| Email | contact@yourdomain.in |
| Phone | +91 00000 00000 |
| Address | Your address line, City, PIN |