2026

Grant Proposal # Mobile Science Lab for Government Schools Bringing hands-on science experiments to 40 schools through a lab-on-wheels

| PREPARED FOR | PREPARED BY | DATE |
| --- | --- | --- |
| Education Grants Committee | Dr. Arvind Kulkarni, Founder Trustee | May 2026 |

# 1. Executive Summary

Most government schools in the district have no functioning science laboratory, so students learn experiments only from textbooks. Jigyasa Education Trust proposes a mobile science lab — a van equipped with apparatus and trained facilitators — that visits 40 schools on a fixed timetable, giving students in Classes 6 to 10 regular hands-on practice.

| 40 Schools | 8,000 Students reached | 2 years Project period |
| --- | --- | --- |

# 2. Background and Need

Science teachers in rural schools often teach without equipment, and students rarely perform experiments themselves. This affects both understanding and interest in science.

A mobile lab can share one well-equipped set of apparatus across many schools at a fraction of the cost of building labs in each.

# 3. Goals and Objectives

Improve understanding of science concepts and curiosity among students in government schools.

Visit each school at least twice a month.

Conduct curriculum-linked experiments for Classes 6–10.

Train science teachers to continue activities between visits.

Organise an annual district science fair.

# 4. Approach and Activities

## Van and equipment

Purchase and fit out the van with apparatus, storage and safety equipment.

## Curriculum mapping

Map 60 experiments to the syllabus for Classes 6–10.

## School visits

Two facilitators run sessions on a fixed timetable.

## Teacher training

Quarterly workshops for science teachers.

## Science fair

District-level fair showcasing student projects.

## Deliverables

| Deliverable | Description | Due |
| --- | --- | --- |
| Equipped van | Lab-on-wheels ready | Month 3 |
| Activity manual | 60 experiments | Month 3 |
| School visits | About 1,600 sessions | Month 24 |
| Teacher workshops | 8 workshops | Month 24 |

# 5. Timeline

The work plan below shows the main activities and their indicative timing.

| Activity | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Van set-up | ■ |  |  |  |  |  |  |  |
| Curriculum mapping | ■ |  |  |  |  |  |  |  |
| School visits |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ |
| Teacher training |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ |
| Science fair |  |  |  | ■ |  |  |  |  |
| Evaluation |  |  |  |  |  |  |  | ■ |

# 6. Team and Governance

| Name | Role | Responsibility |
| --- | --- | --- |
| Dr. Arvind Kulkarni | Project head | Overall responsibility |
| Science facilitators (2) | Facilitators | Sessions in schools |
| Driver-cum-lab assistant | Support | Van and equipment |
| Advisory teacher panel | Advisers | Curriculum and quality |

# 7. Budget

All amounts are estimates in Indian rupees and are provided as sample figures for planning.

| Head | Details | Amount (₹) |
| --- | --- | --- |
| Van and fit-out | One-time | 1,200,000 |
| Apparatus and consumables | Two years | 450,000 |
| Salaries | Facilitators and assistant, two years | 1,680,000 |
| Fuel and maintenance | Two years | 360,000 |
| Teacher workshops and fair | Events | 240,000 |
| Monitoring and admin | Overheads | 200,000 |
| Total |  | 4,130,000 |

# 8. Monitoring and Evaluation

| Indicator | Target | How measured |
| --- | --- | --- |
| Sessions conducted | 1,600 | Visit logs signed by schools |
| Students reached | 8,000 | Attendance |
| Concept test scores | Improvement over baseline | Pre/post tests |
| Teachers trained | 80 | Workshop records |

# 9. Risks and Mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Van breakdown | Medium | Maintenance contract and backup schedule |
| School calendar changes | Medium | Advance timetable with education office |
| Breakage of apparatus | Medium | Spare kits and consumable budget |

# 10. Sustainability

After two years, the trust will seek support from the district administration and local businesses to continue operations, and trained teachers will carry activities forward.

# 11. Conclusion

A mobile science lab is a cost-effective way to make science practical and exciting for thousands of students.

Next step Approve a two-year grant of ₹41.3 lakh to launch the mobile science lab in the coming academic year.

| ____________________ | ____________________ |
| --- | --- |
| Dr. Arvind Kulkarni Submitted by | Approved by (name, designation) |