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Executive Summary
TechVerse is the annual technical festival of Your Institute of Technology, bringing together students from colleges across the region for competitions, workshops and talks. This proposal invites organisations to partner with TechVerse 2026 and connect with a large audience of engineering students.
	2 days
6–7 Feb 2026
	25+
Events
	Regional
Colleges invited



Event Concept
TechVerse gives students a platform to build, compete and learn beyond the classroom. It also gives partners a chance to meet talented students, promote internships and showcase products.
Each edition is planned and run entirely by students, supported by faculty advisers.
Goals and Objectives
Organise a well-run, inclusive technical festival that celebrates innovation and connects students with industry.
Host competitions in coding, robotics, design and entrepreneurship.
Run hands-on workshops led by practitioners.
Provide sponsors with meaningful engagement with students.
Ensure a safe, accessible event for all participants.
Event Details
	Dates
	6–7 February 2026

	Venue
	Main campus, Your Institute of Technology

	Expected footfall
	Several thousand visitors over two days (estimate)

	Participants
	Students from colleges across the region

	Organisers
	Student Council with faculty advisers



Programme Schedule
	Time
	Session
	Venue / format

	Day 1, 9:30 AM
	Inauguration and keynote talk
	Main auditorium

	Day 1, 11:00 AM
	Hackathon kick-off (24 hours)
	Computer centre

	Day 1, 2:00 PM
	Robotics challenge — heats
	Sports complex

	Day 1, 4:00 PM
	Workshop: Intro to IoT
	Lab block

	Day 2, 10:00 AM
	Startup pitch competition
	Seminar hall

	Day 2, 1:00 PM
	Robotics finals
	Sports complex

	Day 2, 5:00 PM
	Prize distribution and closing
	Main auditorium



Target Audience
Undergraduate and postgraduate engineering students
Faculty members and researchers
Early-stage founders and alumni
Sponsorship Opportunities
Sponsors receive visibility before, during and after the event. Packages can be customised; amounts below are indicative.
	Tier
	Contribution
	Key benefits

	Title partner
	₹3,00,000
	Name in event title, keynote slot, logo on all material, stall

	Platinum
	₹1,50,000
	Logo on banners and website, stall, workshop slot

	Gold
	₹75,000
	Logo on banners, social media mentions, stall

	Event partner
	₹40,000
	Naming of one competition, prize distribution

	In-kind partner
	Products / services
	Acknowledgement and stall



Promotion Plan
Social media campaign for six weeks before the fest
Posters and campus ambassadors in partner colleges
Email and newsletter to past participants
Live coverage during the event
Logistics and Operations
	Area
	Plan
	Owner

	Registration
	Online registration with QR entry passes
	Registration team

	Security
	Volunteers and campus security at all gates
	Discipline committee

	Hospitality
	Accommodation for outstation participants
	Hospitality team

	Medical
	First-aid post and ambulance on call
	Medical team



Timeline
The work plan below shows the main activities and their indicative timing.
	Activity
	Oct
	Nov
	Dec
	Jan
	Feb

	Planning and approvals
	■
	■
	
	
	

	Sponsorship drive
	
	■
	■
	■
	

	Promotion
	
	
	■
	■
	■

	Event execution
	
	
	
	
	■

	Post-event report
	
	
	
	
	■



Team and Governance
	Name
	Role
	Responsibility

	Riya Sharma
	General Secretary
	Overall coordination

	Aditya Rao
	Sponsorship head
	Partner relations

	Kavya Iyer
	Events head
	Competitions and schedule

	Prof. S. Banerjee
	Faculty adviser
	Guidance and approvals



Budget
All amounts are estimates in Indian rupees and are provided as sample figures for planning.
	Head
	Details
	Amount (₹)

	Venue and infrastructure
	Stage, sound, lighting
	350,000

	Prizes
	Competition prizes
	250,000

	Hospitality
	Food and accommodation
	220,000

	Promotion
	Printing and digital
	90,000

	Workshops
	Kits and speaker travel
	120,000

	Miscellaneous
	Contingency
	70,000

	Total
	
	1,100,000



Measuring Success
	Indicator
	Target
	How measured

	Registrations
	Target set by council
	Registration system

	Sponsor leads
	Contacts shared with consent
	Lead forms

	Participant feedback
	4 / 5 or higher
	Post-event survey



Risks and Mitigation
	Risk
	Likelihood
	Mitigation

	Weather or power failure
	Low
	Backup generator and indoor venues

	Over-crowding
	Medium
	Entry passes and crowd plan

	Speaker cancellation
	Low
	Backup speakers



Conclusion
Partnering with TechVerse 2026 is an opportunity to engage directly with motivated, skilled students and support innovation on campus.
	Next step
Choose a sponsorship tier or suggest a custom partnership; we will share the agreement and branding guidelines.




	____________________
	____________________

	Riya Sharma
Submitted by
	
Approved by (name, designation)



Annexure: Contact Details
	Organisation
	Student Council, Your Institute of Technology

	Contact person
	Riya Sharma, General Secretary

	Email
	contact@yourdomain.in

	Phone
	+91 00000 00000

	Address
	Your address line, City, PIN
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