Event Proposal

# Swachh Saturday — Neighbourhood Clean-Up Drive

Proposal for a monthly community clean-up and waste-segregation campaign

| PREPARED FOR | PREPARED BY | DATE |
| --- | --- | --- |
| Ward Office and Residents’ Associations | Imran Sheikh, Club Secretary | June 2026 |

# Contents

1. Executive Summary	2

2. Event Concept	3

3. Goals and Objectives	3

4. Event Details	3

Programme Schedule	3

Target Audience	3

5. Sponsorship Opportunities	4

Promotion Plan	4

Logistics and Operations	4

6. Timeline	4

7. Team and Governance	5

8. Budget	5

9. Measuring Success	5

10. Risks and Mitigation	6

11. Conclusion	6

12. Annexure: Contact Details	6

# 1. Executive Summary

The Youth Club proposes a monthly clean-up drive on the first Saturday of every month, combined with door-to-door awareness on waste segregation. The drive will involve residents, schools and local shopkeepers and will be coordinated with the ward office for collection of the waste gathered.

| Monthly First Saturday | 6 lanes Starting area | All ages Volunteers welcome |
| --- | --- | --- |

# 2. Event Concept

Litter in open plots and along the drain near the market is a health risk and an eyesore. Many households are unsure how to segregate wet and dry waste.

A regular, visible community effort can change habits and keep the area clean.

# 3. Goals and Objectives

Create a cleaner neighbourhood through regular community action and better waste habits.

Hold a clean-up drive every month for six months.

Reach every household in the area with segregation information.

Involve at least two schools and the market association.

Reduce littering hotspots.

# 4. Event Details

| Day and time | First Saturday of each month, 7:00–10:00 AM |
| --- | --- |
| Starting point | Community hall, Shanti Nagar |
| Partners | Ward office, schools, market association |
| Equipment | Gloves, bags, rakes from the ward office and club |

## Programme Schedule

| Time | Session | Venue / format |
| --- | --- | --- |
| 7:00 AM | Assembly, safety briefing and team allocation | Community hall |
| 7:20 AM | Clean-up in assigned lanes | Six lanes |
| 9:00 AM | Door-to-door segregation awareness | Residential blocks |
| 9:45 AM | Waste handover to ward vehicle and wrap-up | Community hall |

## Target Audience

Residents of all ages

School students with permission from parents

Shopkeepers and market association

# 5. Sponsorship Opportunities

Sponsors receive visibility before, during and after the event. Packages can be customised; amounts below are indicative.

| Tier | Contribution | Key benefits |
| --- | --- | --- |
| Community supporter | Any amount / in kind | Thanks on notice board and social media |
| Local business partner | ₹5,000 | Banner mention for six months |

## Promotion Plan

Notices in housing societies and at the market

WhatsApp groups of residents’ associations

Announcements in partner schools

## Logistics and Operations

| Area | Plan | Owner |
| --- | --- | --- |
| Safety | Gloves, masks and first-aid kit; no handling of sharp waste by children | Club volunteers |
| Collection | Ward vehicle at 9:45 AM | Ward office |
| Records | Photos and attendance sheet each month | Club secretary |

# 6. Timeline

The work plan below shows the main activities and their indicative timing.

| Activity | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- |
| Planning and permissions | ■ |  |  |  |  |  |
| Monthly drives | ■ | ■ | ■ | ■ | ■ | ■ |
| Awareness visits | ■ | ■ | ■ | ■ | ■ | ■ |
| Review |  |  |  |  |  | ■ |

# 7. Team and Governance

| Name | Role | Responsibility |
| --- | --- | --- |
| Imran Sheikh | Coordinator | Overall planning |
| Pooja Rawat | Volunteer lead | Teams and safety |
| Ward office contact | Partner | Collection support |
| School teachers | Partners | Student volunteers |

# 8. Budget

All amounts are estimates in Indian rupees and are provided as sample figures for planning.

| Head | Details | Amount (₹) |
| --- | --- | --- |
| Gloves and masks | Six months | 12,000 |
| Garbage bags | Six months | 6,000 |
| Banners and notices | Printing | 5,000 |
| Refreshments | Water and snacks for volunteers | 9,000 |
| First aid | Kit refills | 3,000 |
| Total |  | 35,000 |

# 9. Measuring Success

| Indicator | Target | How measured |
| --- | --- | --- |
| Drives held | 6 | Attendance sheets |
| Volunteers per drive | Growing each month | Sign-in sheet |
| Households reached | All in starting area | Visit list |
| Hotspots cleared | Reduced by end of term | Photo record |

# 10. Risks and Mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Monsoon rain | Medium | Reschedule to next Saturday |
| Low turnout | Medium | Involve schools and societies |
| Waste not collected on time | Low | Confirm with ward office the day before |

# 11. Conclusion

Small, regular actions can transform our neighbourhood. We invite everyone to join.

Next step Grant permission and collection support from the ward office for the first drive on 4 July 2026.

| ____________________ | ____________________ |
| --- | --- |
| Imran Sheikh Submitted by | Approved by (name, designation) |

# 12. Annexure: Contact Details

| Organisation | Youth Club, Shanti Nagar |
| --- | --- |
| Contact person | Imran Sheikh, Club Secretary |
| Email | contact@yourdomain.in |
| Phone | +91 00000 00000 |
| Address | Your address line, City, PIN |