Project Proposal # ERP Implementation for Sharma Textiles ——— Proposal for integrating inventory, sales and accounts on a single cloud ERP PREPARED FOR Management, Sharma Textiles Pvt. Ltd. PREPARED BY Ananya Desai, Engagement Manager DATE February 2026

# Contents

01  Executive Summary	2

02  Background and Need	3

03  Goals and Objectives	3

04  Approach and Activities	3

Discovery	3

Configuration	3

Data migration	3

Testing and training	3

Go-live and support	4

Deliverables	4

05  Timeline	4

06  Team and Governance	4

07  Budget	5

08  Monitoring and Evaluation	5

09  Risks and Mitigation	5

10  Assumptions	6

11  Conclusion	6

12  Annexure: Contact Details	6

# 01  Executive Summary

Sharma Textiles runs inventory, sales and accounts on separate spreadsheets and a legacy desktop package, which causes stock mismatches and delays in month-end closing. Northfield Consulting proposes a phased implementation of a cloud ERP covering inventory, purchase, sales, GST-ready accounting and dashboards, delivered in 20 weeks with training and three months of support.

| 20 weeks Implementation | 5 modules In scope | 3 months Post-go-live support |
| --- | --- | --- |

# 02  Background and Need

The business has grown to three warehouses and over 400 active customers. Data is entered several times in different systems, so stock levels and receivables are often out of date.

Management needs a single view of stock, orders and cash to plan production and purchasing confidently.

Stock mismatches between warehouses

Month-end closing takes about 12 days

No real-time view of receivables

# 03  Goals and Objectives

Give Sharma Textiles one reliable system for operations and finance.

Integrate inventory across three warehouses.

Automate sales orders, invoicing and GST reports.

Reduce month-end closing time.

Provide management dashboards.

# 04  Approach and Activities

## Discovery

Workshops with each department to map current processes and pain points.

## Configuration

Set up masters, workflows, approval rules and reports.

## Data migration

Clean and migrate item, customer, supplier and opening balance data.

## Testing and training

User acceptance testing with real scenarios and role-based training.

## Go-live and support

Cut-over plan, hyper-care and three months of support.

## Deliverables

| Deliverable | Description | Due |
| --- | --- | --- |
| Process blueprint | Future-state process maps | Week 4 |
| Configured ERP | All modules in test | Week 12 |
| Migrated data | Verified masters and balances | Week 15 |
| Trained users | Role-based sessions | Week 18 |
| Go-live | Production system | Week 20 |

# 05  Timeline

The work plan below shows the main activities and their indicative timing.

| Activity | W1–4 | W5–8 | W9–12 | W13–16 | W17–20 |
| --- | --- | --- | --- | --- | --- |
| Discovery | ■ |  |  |  |  |
| Configuration |  | ■ | ■ |  |  |
| Data migration |  |  | ■ | ■ |  |
| Testing and training |  |  |  | ■ | ■ |
| Go-live |  |  |  |  | ■ |

# 06  Team and Governance

| Name | Role | Responsibility |
| --- | --- | --- |
| Ananya Desai | Engagement manager | Delivery and client communication |
| Rahul Bhat | Functional consultant | Inventory and sales |
| Sonal Shah | Finance consultant | Accounts and GST |
| Client process owners | Key users | Decisions and testing |

A fortnightly steering meeting with the client’s directors will track milestones, risks and decisions.

# 07  Budget

All amounts are estimates in Indian rupees and are provided as sample figures for planning.

| Head | Details | Amount (₹) |
| --- | --- | --- |
| Consulting fees | Discovery, configuration and testing | 950,000 |
| Data migration | Cleaning and loading | 180,000 |
| Training | On-site sessions and manuals | 120,000 |
| Support | Three months post go-live | 150,000 |
| Total |  | 1,400,000 |

# 08  Monitoring and Evaluation

| Indicator | Target | How measured |
| --- | --- | --- |
| Stock accuracy | 98% | Cycle counts |
| Month-end closing | ≤ 5 days | Finance calendar |
| Order-to-invoice time | Same day | ERP reports |
| User adoption | 100% transactions in ERP | System audit |

# 09  Risks and Mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Poor data quality | High | Data cleaning sprint before migration |
| Key users unavailable | Medium | Agreed time commitment per week |
| Scope creep | Medium | Change-request process |

# 10  Assumptions

The client will provide a project coordinator, timely access to data and availability of key users for workshops and testing. Licence costs for the ERP are billed separately by the software provider.

# 11  Conclusion

A well-implemented ERP will give Sharma Textiles accurate stock, faster closing and better decisions. We look forward to partnering on this transformation.

Next step Sign the engagement letter so that the discovery workshops can start on the agreed date.

| ____________________ | ____________________ |
| --- | --- |
| Ananya Desai Submitted by | Approved by (name, designation) |

# 12  Annexure: Contact Details

| Organisation | Northfield Consulting |
| --- | --- |
| Contact person | Ananya Desai, Engagement Manager |
| Email | contact@yourdomain.in |
| Phone | +91 00000 00000 |
| Address | Your address line, City, PIN |