Project Proposal

# Campus-Wide Smart Attendance System

Proposal to replace paper registers with a QR- and app-based attendance platform

| PREPARED FOR | PREPARED BY | DATE |
| --- | --- | --- |
| The Principal and Academic Council | Dr. Kavya Menon, Project Coordinator | March 2026 |

# Executive Summary

Teachers currently spend several minutes of every lecture marking attendance on paper, and the data reaches the office weeks later. This proposal requests approval and funding to build and roll out a smart attendance system that lets students mark attendance by scanning a rotating QR code in class, with location and time checks to prevent proxies. Teachers get instant class reports and the office gets monthly shortage lists automatically.

| 6 months Development and roll-out | ₹4.6 L Estimated budget | 3,200 Students covered |
| --- | --- | --- |

# Background and Need

Paper attendance takes time away from teaching, is easy to manipulate and is difficult to analyse. Monthly shortage lists are prepared by hand, which delays communication with students and parents.

A digital system would save teaching time, improve accuracy and allow early support for students with poor attendance.

About 5–7 minutes per lecture spent on roll call (estimate)

Registers stored in different departments

Shortage lists prepared manually every month

# Goals and Objectives

Introduce a reliable, low-cost digital attendance system for all departments within one academic semester.

Reduce time spent on attendance to under one minute per lecture.

Generate department and student-wise reports automatically.

Alert students and mentors when attendance falls below 75%.

Keep student data secure and accessible only to authorised staff.

# Approach and Activities

## Requirement study

Interview teachers, office staff and students; study existing registers and rules.

## Design and development

Build the teacher app, student app and admin dashboard with role-based access.

## Pilot

Run a four-week pilot in two departments and collect feedback.

## Roll-out and training

Train all faculty, publish user guides and roll out college-wide.

## Deliverables

| Deliverable | Description | Due |
| --- | --- | --- |
| Requirement document | Agreed features and rules | Month 1 |
| Working apps | Teacher and student mobile apps | Month 3 |
| Admin dashboard | Reports and alerts | Month 4 |
| Pilot report | Findings and fixes | Month 5 |
| Training material | Guides and videos | Month 6 |

# Timeline

The work plan below shows the main activities and their indicative timing.

| Activity | M1 | M2 | M3 | M4 | M5 | M6 |
| --- | --- | --- | --- | --- | --- | --- |
| Requirement study | ■ |  |  |  |  |  |
| Design | ■ | ■ |  |  |  |  |
| Development |  | ■ | ■ | ■ |  |  |
| Pilot |  |  |  |  | ■ |  |
| Training and roll-out |  |  |  |  | ■ | ■ |

# Team and Governance

| Name | Role | Responsibility |
| --- | --- | --- |
| Dr. Kavya Menon | Coordinator | Overall responsibility and reporting |
| Mr. Arjun Pillai | Technical lead | Architecture and development |
| Student developers (4) | Developers | Apps and dashboard |
| Office superintendent | Process owner | Rules and reports |

A steering group chaired by the Vice-Principal will review progress every month.

# Budget

All amounts are estimates in Indian rupees and are provided as sample figures for planning.

| Head | Details | Amount (₹) |
| --- | --- | --- |
| Cloud hosting (1 year) | Server, database and backups | 60,000 |
| Development support | Stipends for student developers | 180,000 |
| Devices | Tablets for classrooms without projectors | 120,000 |
| Training | Workshops and guides | 40,000 |
| Contingency | About 10% | 60,000 |
| Total |  | 460,000 |

# Monitoring and Evaluation

| Indicator | Target | How measured |
| --- | --- | --- |
| Time per roll call | < 1 minute | Classroom observation |
| Adoption | 90% of lectures | System logs |
| Report accuracy | 99% | Audit against sample registers |
| User satisfaction | 4 / 5 | Survey after pilot |

# Risks and Mitigation

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Poor network in some rooms | Medium | Offline mode with later sync |
| Resistance to change | Medium | Training and champions in each department |
| Proxy attempts | Low | Rotating QR plus location checks |

# Conclusion

The smart attendance system is a practical, affordable step that saves teaching time and helps students who are falling behind. We request approval to begin the requirement study in April.

Next step Approve the proposal and the budget of ₹4.6 lakh so that work can begin next month.

| ____________________ | ____________________ |
| --- | --- |
| Dr. Kavya Menon Submitted by | Approved by (name, designation) |